Project Manager: Ryan Coffee
Date: 03/18/19
2D-TimeTool/LDRD Project Overview
Major Milestones*
Project Scope and deliverables
Milestones	Planned date	Current date	Comment
EdgeML nodes	03/2018	06/2018
2D 10kfps camera	10/2018	11/2018
ML development environment	10/2019
Project Completion	10/01/2019	12/31/2019	Late start
2D sub-fs resolution timing system as a demonstration case for Machine Learning for data reduction at LCLS-II
Standardized machine learning development environment with a target of FPGA-based inference for data compression and veto
Prototype EdgeML server nodes (x2) with heterogeneous CPU/GPU/FPGA acceleration for combining simulation and ML training
Prototype 2D visible light sensor compatible with higher than 10kfps acquisition
Project Team
Role	Name	% FTE	Status
Project Manager	Ryan Coffee	20%	Committed
IT/ML	Abdullah Rashed Ahmed	20%	Committed
IT/ML	Omar Quijano	20%	Committed
Students	T. Aiken	50%	Committed
Cost
	FY18	FY19	Total
PEC approved	$ 314 k	$ xxx k	$ xxx k
Actuals	$ 314 k	$ xxx k	$ xxx k
* Please update or/and add different/other relevant milestones for your project